## Sheet1
Application | # | Module | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource
Airline System (Online Ticket Booking) | 1 | Login | Analysis | Requirement Analysis | 2 | 2017-11-07 | 2017-11-07 | 2 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing QFB | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2017-11-07 | 2017-11-09 | 4 | 2017-11-07 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  | Design | Unit Test Plan Preparation | 2 | 2017-11-09 | 2017-11-09 | 1.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Preparation | 2 | 2017-11-09 | 2017-11-09 | 1.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Review | 1 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Rework | 1 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Review | 1.5 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Rework | 1 | 2017-11-09 | 2017-11-10 | 0.5 | 2017-11-09 | 2017-11-10 | Vaishali Srivastava, Vishal Mali
|  |  | Build | Coding | 10 | 2017-11-10 | 2017-11-13 | 10 | 2017-11-10 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Self Review | 2 | 2017-11-13 | 2017-11-13 | 1.5 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Self Testing | 2 | 2017-11-13 | 2017-11-13 | 1 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-13 | 2017-11-13 | 0.5 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Peer Review | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Peer Testing | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 2 | 2017-11-14 | 2017-11-14 | 1.5 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 3 | 2017-11-14 | 2017-11-14 | 1 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Integration | 2 | 2017-11-14 | 2017-11-14 | 3 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Integration Testing | 1 | 2017-11-14 | 2017-11-15 | 1 | 2017-11-14 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-15 | 2017-11-15 | 3 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 1 | 2017-11-15 | 2017-11-15 | 1 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Total Planned Hrs : | 49.5 |  | Total Actual Hrs:
Airline System (Online Ticket Booking) | 2 | Registration | Analysis | Requirement Analysis | 2 | 2017-11-07 | 2017-11-07 | 2 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing QFB | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2017-11-07 | 2017-11-09 | 4 | 2017-11-07 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  | Design | Unit Test Plan Preparation | 2 | 2017-11-09 | 2017-11-09 | 1.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Preparation | 2 | 2017-11-09 | 2017-11-09 | 2 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Review | 1 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Rework | 1 | 2017-11-09 | 2017-11-09 | 1 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Review | 1.5 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Rework | 1 | 2017-11-09 | 2017-11-10 | 1 | 2017-11-09 | 2017-11-10 | Vaishali Srivastava, Vishal Mali
|  |  | Build | Coding | 15 | 2017-11-10 | 2017-11-13 | 10 | 2017-11-10 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Self Review | 2 | 2017-11-13 | 2017-11-13 | 2 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Self Testing | 2 | 2017-11-13 | 2017-11-13 | 2 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-13 | 2017-11-13 | 1.5 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Peer Review | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Peer Testing | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 3 | 2017-11-14 | 2017-11-14 | 2.5 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Integration | 2 | 2017-11-14 | 2017-11-14 | 3 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Integration Testing | 1 | 2017-11-14 | 2017-11-15 | 1 | 2017-11-14 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-15 | 2017-11-15 | 3 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 1 | 2017-11-15 | 2017-11-15 | 1 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Total Planned Hrs : | 54.5 |  | Total Actual Hrs:
Airline System (Online Ticket Booking) | 3 | Search Flight | Analysis | Requirement Analysis | 2 | 2017-11-07 | 2017-11-07 | 2 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing QFB | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2017-11-07 | 2017-11-09 | 2 | 2017-11-07 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  | Design | Unit Test Plan Preparation | 3 | 2017-11-09 | 2017-11-09 | 2.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Preparation | 3.5 | 2017-11-09 | 2017-11-09 | 3.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Review | 1 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Rework | 1 | 2017-11-09 | 2017-11-09 | 1 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Review | 1.5 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Rework | 1.5 | 2017-11-09 | 2017-11-10 | 1.5 | 2017-11-09 | 2017-11-10 | Vaishali Srivastava, Vishal Mali
|  |  | Build | Coding | 10 | 2017-11-10 | 2017-11-13 |  | 2017-11-10 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Self Review | 2 | 2017-11-13 | 2017-11-13 |  | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Self Testing | 2 | 2017-11-13 | 2017-11-13 |  | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-13 | 2017-11-13 |  | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Peer Review | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Peer Testing | 2 | 2017-11-14 | 2017-11-14 | 1.5 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 2 | 2017-11-14 | 2017-11-14 |  | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 3 | 2017-11-14 | 2017-11-14 |  | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Integration | 2 | 2017-11-14 | 2017-11-14 | 3 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Integration Testing | 1 | 2017-11-14 | 2017-11-15 | 1 | 2017-11-14 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-15 | 2017-11-15 | 3 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 1 | 2017-11-15 | 2017-11-15 | 1 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Total Planned Hrs : | 52.5 |  | Total Actual Hrs:
Airline System (Online Ticket Booking) | 4 | Confirm Booking | Analysis | Requirement Analysis | 2 | 2017-11-07 | 2017-11-07 | 2 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing understanding Document & Reverse Presentation | 3 | 2017-11-07 | 2017-11-07 | 3 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Preparing QFB | 1 | 2017-11-07 | 2017-11-07 | 1 | 2017-11-07 | 2017-11-07 | Vaishali Srivastava, Vishal Mali
|  |  |  | Understanding HLD/Class Diagram Prep | 4 | 2017-11-07 | 2017-11-09 | 4 | 2017-11-07 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  | Design | Unit Test Plan Preparation | 1.5 | 2017-11-09 | 2017-11-09 | 1.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Preparation | 2 | 2017-11-09 | 2017-11-09 | 2 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Review | 1 | 2017-11-09 | 2017-11-09 | 1 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | UTP Rework | 1 | 2017-11-09 | 2017-11-09 | 1 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Review | 1.5 | 2017-11-09 | 2017-11-09 | 0.5 | 2017-11-09 | 2017-11-09 | Vaishali Srivastava, Vishal Mali
|  |  |  | LLD Rework | 1 | 2017-11-09 | 2017-11-10 | 1 | 2017-11-09 | 2017-11-10 | Vaishali Srivastava, Vishal Mali
|  |  | Build | Coding | 10 | 2017-11-10 | 2017-11-13 | 12 | 2017-11-10 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Self Review | 2 | 2017-11-13 | 2017-11-13 | 1.5 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Self Testing | 2 | 2017-11-13 | 2017-11-13 | 1.5 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-13 | 2017-11-13 | 1 | 2017-11-13 | 2017-11-13 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Peer Review | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Peer Testing | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 2 | 2017-11-14 | 2017-11-14 | 2 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 3 | 2017-11-14 | 2017-11-14 | 3 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Code Integration | 2 | 2017-11-14 | 2017-11-14 | 3 | 2017-11-14 | 2017-11-14 | Vaishali Srivastava, Vishal Mali
|  |  |  | Integration Testing | 1 | 2017-11-14 | 2017-11-15 | 1 | 2017-11-14 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Rework | 2 | 2017-11-15 | 2017-11-15 | 3 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Test Result review | 1 | 2017-11-15 | 2017-11-15 | 1 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Total Planned Hrs : | 49 |  | Total Actual Hrs:
|  | Presentation Preparation |  | Presentation Preparation | 4 | 2017-11-15 |  | 4 | 2017-11-15 | 2017-11-15 | Vaishali Srivastava, Vishal Mali
|  |  |  | Deployment | 1